## Sheet1
SEVERITY
| Risk | Result of risk | known problems | Likelihood | Impact | Risk Level | mitigation | Likelihood | Impact | Risk Level |  |  | Minimal | Minor | Moderate | Major | Severe
1 | covid-19 | death wont finish project | pandemic is ongoing | 2 | 4 | 8 | mask distance | 1 | 1 | 1 | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
2 | Power outage | Loss of unsaved files Loss of time | Have to redo work | 2 | 8 | 16 | frequent pushes to github | 2 | 1 | 2 |  | Expected | 4 | 8 | 12 | 16 | 20
3 | internet outage | Loss of unsaved files loss of time | Have to redo work | 2 | 8 | 16 | frequent pushes to github | 2 | 1 | 2 |  | Likely | 3 | 6 | 9 | 12 | 15
4 | Lack of testing | code that doesn’t work properly | unfinished project | 3 | 12 | 36 | get 80% coverage | 2 | 6 | 12 |  | Possible | 2 | 4 | 6 | 8 | 10
5 | corrupted files | lost time | have to fix or reinstall software | 2 | 4 | 8 | frequent saves frequent pushes to github | 2 | 1 | 2 |  | Unlikely | 1 | 2 | 3 | 4 | 5
6 | Poor time management | wont finish project | wont meet project requirments | 2 | 6 | 12 | plan out the project | 2 | 2 | 4
7 | unneeded code "Gold plating" | the code will break wasted time | wont meet project requirments | 1 | 3 | 3 | don’t add unneeded code | 1 | 1 | 1
8